## Projects
Project ID | Project name | Report date | Status | Project start | Project end | Phase | Completion percent | Project manager | Client | Currency | Budget | Spent | Budget remaining | Budget utilization | Client approved | On budget | Summary | Risks | Next steps
PRJ-2026-07 | ERP migration for Rheinwerk | 2026-10-01 | On track | 2026-05-04 | 2026-12-18 | Build | 62 | Anna Kowalski | Rheinwerk Industrietechnik GmbH | EUR | 240000 | 141600 | 98400 | 59 | TRUE | TRUE | Data migration scripts are complete and tested on two of the four plants. | Plant 3 has custom fields that still need mapping. Key users are less available in November. | Start user acceptance testing at plants 1 and 2.
PRJ-2026-08 | Clinic reporting pilot | 2026-10-05 | At risk | 2026-09-01 | 2026-11-30 | Pilot | 35 | Daniel Okafor | Lumen Health Partners | CAD | 60000 | 31200 | 28800 | 52 | FALSE | FALSE | Two of the three clinics are live. The third is waiting for the privacy review. | The privacy review may delay the third clinic by three weeks. | Escalate the privacy review to the client sponsor.
PRJ-2026-09 | Client portal for Atelier Moreau | 2026-10-08 | On track | 2026-08-17 | 2026-11-27 | Design | 48 | Emily Carter | Atelier Moreau SARL | EUR | 38000 | 16500 | 21500 | 43 | TRUE | TRUE | The portal design is approved. Development of the approval flow has started. | French translations depend on the client's copywriter. | Deliver the first build for review on 23 October.
PRJ-2026-10 | Warehouse automation, Lagos | 2026-10-12 | Delayed | 2026-06-01 | 2027-02-26 | Installation | 41 | Grace Wanjiru | Oduya Logistics Ltd | USD | 410000 | 236000 | 174000 | 58 | TRUE | FALSE | Conveyor installation is four weeks behind because of customs clearance. | More customs delays; freight costs above budget. | Agree a revised installation plan with the client.
PRJ-2026-11 | Data connector rollout | 2026-10-15 | On track | 2026-10-01 | 2026-11-13 | Build | 30 | Sofia Alvarez | Southern Cross Analytics | AUD | 52000 | 12400 | 39600 | 24 | TRUE | TRUE | The Snowflake connector is live. BigQuery is in testing. | Salesforce API limits on the client's edition. | Confirm the Salesforce edition with the client.

## ProjectTeam
Project ID | Name | Role | Department | Email | Allocation percent
PRJ-2026-07 | Anna Kowalski | Project Manager | PMO | anna.kowalski@acme-corp.example | 50
PRJ-2026-07 | Jonas Weber | Lead Consultant | Delivery | jonas.weber@acme-corp.example | 100
PRJ-2026-07 | Mei Lin Chen | Data Engineer | Engineering | meilin.chen@acme-corp.example | 80
PRJ-2026-08 | Daniel Okafor | Project Manager | Delivery | daniel.okafor@acme-corp.example | 60
PRJ-2026-08 | Sarah Nguyen | Reporting Analyst | Analytics | sarah.nguyen@acme-corp.example | 100
PRJ-2026-08 | Tom Harris | Trainer | Training | tom.harris@acme-corp.example | 40
PRJ-2026-09 | Emily Carter | Project Manager | Delivery | emily.carter@acme-corp.example | 40
PRJ-2026-09 | Nadia Haddad | Product Designer | Design | nadia.haddad@acme-corp.example | 100
PRJ-2026-09 | Thomas Müller | Developer | Engineering | thomas.muller@acme-corp.example | 80
PRJ-2026-10 | Grace Wanjiru | Project Manager | PMO | grace.wanjiru@acme-corp.example | 100
PRJ-2026-10 | Samuel Osei | Automation Engineer | Engineering | samuel.osei@acme-corp.example | 100
PRJ-2026-10 | Liam O'Connor | Procurement Specialist | Procurement | liam.oconnor@acme-corp.example | 30
PRJ-2026-11 | Sofia Alvarez | Project Manager | Delivery | sofia.alvarez@acme-corp.example | 50
PRJ-2026-11 | Thomas Müller | Developer | Engineering | thomas.muller@acme-corp.example | 60
PRJ-2026-11 | Sarah Nguyen | Data Analyst | Analytics | sarah.nguyen@acme-corp.example | 50

## ProjectMilestones
Project ID | Milestone name | Due date | Status | Completion percent | Owner
PRJ-2026-07 | Requirements signed off | 2026-06-12 | Done | 100 | Anna Kowalski
PRJ-2026-07 | Data migration scripts | 2026-09-25 | Done | 100 | Mei Lin Chen
PRJ-2026-07 | User acceptance testing | 2026-11-13 | In progress | 20 | Jonas Weber
PRJ-2026-07 | Go-live | 2026-12-18 | Not started | 0 | Anna Kowalski
PRJ-2026-08 | Clinic 1 live | 2026-09-21 | Done | 100 | Sarah Nguyen
PRJ-2026-08 | Clinic 2 live | 2026-09-28 | Done | 100 | Sarah Nguyen
PRJ-2026-08 | Privacy review | 2026-10-16 | In progress | 50 | Daniel Okafor
PRJ-2026-08 | Clinic 3 live | 2026-11-02 | Not started | 0 | Sarah Nguyen
PRJ-2026-09 | Design approved | 2026-09-18 | Done | 100 | Nadia Haddad
PRJ-2026-09 | Approval flow built | 2026-10-30 | In progress | 40 | Thomas Müller
PRJ-2026-09 | French translation | 2026-11-13 | Not started | 0 | Emily Carter
PRJ-2026-10 | Site survey | 2026-06-19 | Done | 100 | Samuel Osei
PRJ-2026-10 | Equipment delivered | 2026-09-11 | Done | 100 | Liam O'Connor
PRJ-2026-10 | Conveyor installation | 2026-11-20 | In progress | 30 | Samuel Osei
PRJ-2026-10 | Commissioning | 2027-02-12 | Not started | 0 | Grace Wanjiru
PRJ-2026-11 | Snowflake connector | 2026-10-09 | Done | 100 | Thomas Müller
PRJ-2026-11 | BigQuery connector | 2026-10-23 | In progress | 60 | Thomas Müller
PRJ-2026-11 | Salesforce connector | 2026-11-06 | Not started | 0 | Sarah Nguyen